## Sheet1
Card | Story | Back of the card: | Tasks: | Status
Card 1 | As a user I want to view a recipe so I can prepare a meal. | A recipe would contain both a list of ingredients and a list of steps. This could be represented by a class object in Java. We will probably have multiple recipes in the system so we need some type of list or pool to contain all of them. A recipe should also have an ID. | Create a class for a recipe that contains a list of ingredients and a list of steps. | Done
|  |  | Create a RecipePool that can hold all recipes. | Done
|  |  | Create some type of method for displaying a recipe. Create a method in RecipePool class which can return recipe based on ID, Method name can be getRecipeByID. | Done
|  |  | Add 8 mockup recipes to the RecipePool that we can use for testing. | Done
Card 2 | As a user I want to be able to generate a food schedule for each week since I don´t have time to plan everything myself. | We could pick 7 random recipes from the RecipePool. These should be stored in the text file userdata.txt with the week number. | Create function to select 7 random recipes from the RecipePool and store them in userdata.txt when user generates new week. | Done
|  |  | The week number should automatically be increased when user generates new recipe week. | Done
Card 3 | As a user I don't want to eat the same dish every day, since this is not healthy. | We need to add some type of algorithm such that a recipe does not show up twice in a row. The recipe for a week should be generated automatically but recipe should not be repeated. | Create a function which can return unique list of randomly selected recipes from the recipe pool. | Done
|  |  | Use this function to get sub list of recipes from the recipe pool to generate new week. | Done
Card 4 | As a user I want to view all the weeks that are already generated for me. | We need to add a menu option for the user, user should be able to select that option and view all the weeks that are generated. | Create menu option for the user "List my weeks" | Done
|  |  | User should be able to list all the weeks those are generated | Done
|  |  | User should also be able to view the recipe from the list of weeks | Done
|  |  | There should be option to view recipe form the list of generated weeks. | Done
Card 5 | As a user/dietician I want to view list of all the available recipes. | We need to add a menu option for the user and dietician they should be able view all the available recipes in the recipe pool. | Create menu option for the user "List recipes" | Done
|  |  | User and Dietician should be able to list all the available recipes | Done
|  |  | Create a function which list all the recipes from the available recipe pool. | Done
Card 6 | As a dietician I want to view a particular recipe using recipe ID. | We need to add a menu option for the dietician, dietician should be able view the recipe using the recipe ID. | Create menu option for the dietician as "View recipe" | Done
|  |  | Dietician should be able to enter a valid recipe ID and view the recipe. In the prompt provide some guide to enter valid recipe ID. | Done
|  |  | Reuse the view recipe function in the recipe class to view recipe for the dietician. | Done
Card 7 | There should be a option to switch to Dietician from the user menu and vice versa. | We need to add an option in both user menu and Dietician menu through which user and dietician will be able to switch to other role. | Create menu option in the menu option for user as Switch to Dietician and in Dietician menu as Switch to User | Done
|  |  | Data loss should not occur during user switch i.e. if a Dietician have created a recipe then it should be preserved if user is switched and if a user have generated a week then it should be preserved when switching to Dietician. | Done
Card 8 | As a dietician I want to create a new recipe and add it to the recipe pool. | We need to add a menu option for the dietician, dietician should be able to select that menu option and create a new recipe. The recipe should be stored and it should be available for view and also should be available for selection for generate new week function when the user generates a new week. | Create a class which can handle and take all the inputs that are required to create a new recipe. | Done
|  |  | When dietician is creating new recipe there should be validation on measurement type, it should allow only provided values (kg, l and pc) | Done
|  |  | Dietician should be able to input 1 or more ingredients. | Done
|  |  | Dietician should be able to input 1 or more steps. | Done
|  |  | The recipe should be saved and recipe id should be automatically generated. | Done
Card 9 | As a dietician I want to edit an exiting recipe, I should be able to add/delete ingredients and also add/delete steps. | We need to add a menu option for the dietician, dietician should be able to select that menu option and edit an existing recipe. | Create a new class to view the edit recipe options for the dietician. | Done
|  |  | The dietician should be able to select the recipe to edit. | Done
|  |  | After the recipe is selected the present the dietician with following options - 1. Add Ingredients 2. Delete Ingredients 3. Add Steps 4. Delete Steps | Done
|  |  | Reuse the functionality of create recipe to get input from the user to add ingredients/steps | Done
|  |  | Create a class which can edit the stored data after dietician have completed the add/delete selection | Done